## Technical Track
# |  | Tasks | Start Date | End Date | Assigned To | Status | Comment
Build Dev
Pre Requisite for Cloudera Installation
|  | Comlete Pre Requisite for Dev Env - Root Access to servers, Database for repository | 2019-04-05 | 2019-04-07 | Cloudera/Team | Completed
Install Cloudera CDH5
|  | Enable SSH across all nodes | 2019-04-26 | 2019-04-27 | Cloudera/Team | Not Completed
|  | Install Cloudera Manager, Agents, demons | 2015-04-18 | 2015-04-18 | Cloudera/Team | Completed
|  | Setup Cloudera Metastore Repository on Oracle Database |  |  | Cloudera/Team | Not Completed | Connectivity issue with Oracle Database/ Timeout issue
|  | Setup Cloudera Metastore Repository on MySQL | 2019-04-18 | 2019-04-18 | Cloudera/Team | Completed
|  | Install CDH 6.2 | 2019-04-25 | 2019-04-25 | Cloudera/Team | Working
Setup Security
|  | Security Setup - Enable SSL for CM, Hue, Navigator, Impala | 2019-04-26 | 2019-04-27 | Cloudera/Team | Not Completed
|  | Security Setup - Active Directory/LDAP authentication setup for Hue completed | 2019-04-29 | 2019-04-30 | Cloudera/Team | Not Completed
|  | Setup MySQL Master-Slave and tested sucessfully. | 2019-05-01 | 2019-05-01 | Cloudera/Team | Not Completed
|  | Dev environment connectivity test with different source systems is in progress | 2019-05-02 | 2019-05-02 | Cloudera/Team | Not Completed
|  | Setup dynamic resource allocation for yarn | 2019-05-03 | 2019-05-03 | Cloudera/Team | Not Completed
Setting up Cloudera Access Governance
|  | Sentry Setup | 2019-05-06 | 2019-05-06 | Cloudera/Team | Not Completed
|  | Integration of Active directory with Kerberos | 2019-05-07 | 2019-05-07 | Cloudera/Team | Not Completed
|  | Platform optimization | 2019-05-08 | 2019-05-08 | Cloudera/Team | Not Completed
|  | Add Edge and Master-2 into Cluster | 2019-05-09 | 2019-05-09 | Cloudera/Team
|  | Move MySQL passive from DataNode to Stand-by Master | 2019-05-09 | 2019-05-09 | Cloudera/Team | Not Completed
Testing
Perform end-to-end Testing
|  | Complete RND Dev Envirnment | 2019-05-10 | 2019-05-11 | Cloudera/Team | Not Completed
|  | create application and admin related AD Groups | 2019-05-10 | 2019-05-10