## Slide 1
3.5 weeks
4 weeks
1 weeks
QA Environment Build
Pre-Requisite/
Pre-Build Phase
Production Environment Build
Development Environment Build
3.5 weeks
18-Mar
23-Mar
25-Mar
23- Apr
16-Apr
08-May
08-May
31-May
25-Mar
16-Apr
29-Mar
09-Apr
09-Apr
Build Development cluster
01-Apr
Security Setup
Dev Env. Connectivity test
12-Apr
Governance build
Platform Optimization
E2E testing
15-Apr
Dev Env Available
Hyper Care
16-Apr
08-May
19-Apr
26-Apr
29-Apr
Build QA cluster
Prepare IQOQ documents
22-Apr
06-May
Security Setup
QA Env. Connectivity test
Execute IQOQ documents
08-May
Hyper Care
R&D Data Lake Build: Timeliness to new Infrastructure
Governance build
Platform Optimization
Submit IQOQ approvals
E2E testing
QA Env Available
03-May
08-May
31-May
16-May
22-May
22-May
Build PRODUCTION cluster
Prepare IQOQ documents
16-May
29-May
Create new EDL storage
Start Data Transfer to new cluster
Execute IQOQ documents
31-May
Hyper Care
Governance build
Platform Optimization
Submit IQOQ approvals
E2E testing
QA Env Available
29-May