## Pre Upgrade
S.No. | Date | Action Item
1 | 12th April 2019 | Apply for root access in Myapps for the PROD server
2 |  | Calculate Navigator Metadata Server Heap Size for Upgrade Link: https://cloudera-portal.force.com/articles/KB_Article/Navigator-Metadata-Server-Exits-Unexpectedly-Heap-Size-Upgrade-Issue-TsP?popup=false&navBack=H4sIAAAAAAAAAIuuVipWslLyzssvz0lNSU_1yM9NVdJRygaKFSSmp4ZkluSA-KVAvn58aaZ-NkyhPpCDosu-ODWxKDnD1i-xLDM9sSS_SNs3tSQxJbEkUbs4tagstUg7IzWxQKk2FgDrDdwFcwAAAA https://itsusralsp07966.jnj.com:7187/debug https://itsusralsp07966.jnj.com:7187/solr Choose nav_elements and note the value of num Docs Choose nav_relations and note the value of num Docs (200 * nav_elements) + (200 * nav_relations) = solr data structure + 2Gb
3 |  | Run Navigator clean up API's before upgrading CM and the cluster Steps: Purge API: curl -X POST -u 'userid:password' "https:// itsusralsp07935.jnj.com:7187/api/v9/maintenance/purge?deleteTimeThresholdMinutes=43200" --cacert /opt/cloudera/security/CAcerts/combinedtrust.pem Status API: curl -X GET -u 'userid:password' "https:// itsusralsp07935.jnj.com:7187/api/v9/maintenance/running" --cacert /opt/cloudera/security/CAcerts/combinedtrust.pem History API: curl -X GET -u 'userid:password' "https:// itsusralsp07935.jnj.com:7187/api/v9/maintenance/history?offset=0&limit=100" --cacert /opt/cloudera/security/CAcerts/combinedtrust.pem
4 |  | hdfs fsck / hdfs dfsadmin -report hbase hbck Check if there is anything missing or lost blocks
5 |  | Capture API output in a txt file: https://edlcmprod.jnj.com:7183/api/v16/cm/deployment
6 |  | Send out service advisory just before the upgrade
7 |  | Upload diagnostic bundle with a size of 2048 MB to Cloudera before the upgrade: Add comment "Before upgrade to CDH 5.15.2" in the diagnostic comments section
8 |  | Run a host inspector in CM before starting the upgrade. Capture the results. Download it and save
9 |  | Take SQL Backup after shutting down the cluster - Approximate run time 1.5 hours

## Upgrade Steps
Date | StartTime | EndTime | Activity | Resources | Status | Comments for EDL upgrade
29th March 2019 | 18:00 | 1:00 | Make sure that the users are logged off and no jobs are running
Shutdown the cluster services and cloudera manager services
Stop agents on all the servers: service cloudera-scm-agent stop service cloudera-scm-agent status --------------------------------------------------------------------------- On itsusralsp07966.jnj.com stop the Server service cloudera-scm-server stop service cloudera-scm-server status
Take backup of Mysql before doing the upgrade Perfrom the steps on all the nodes on by one ITSUSRALSP07969.jnj.com and ITSUSRALSP08030.jnj.com cd /apps/EDL_Admin/scripts/bar/scripts/db_bkp.sh or to execute directly : sh -x /apps/EDL_Admin/scripts/bar/scripts/db_bkp.sh FULL crontab -l sh -x db_bkp.sh FULL check for the DUmps Directory for the Backup To make sure the back up is present please check below location: cd /data/data02/dbbackup/ Example : full_bkp_26_03_2019_05_00_01.tar.gz with upgrade date should be present . This is just an example.
Service mysqld status service mysqld stop
Now need to take Name node a backup ------------------ Check for both name node : itsusralsp07967.jnj.com or itsusralsp07968.jnj.com locate nn ¦ more cd /data/data01/dfs/nn/current if there is any backed up NN move it to upgrade folder tar -cvf /apps/nn_bkp/nn_bkp.tar . Validate the backup has been copied cd /apps/nn_bkp
Java Upgrade is not needed as cluster is already on 1.8.74
lets upgrade all the nodes export LD_LIBRARY_PATH=/lib:/usr/lib cd /etc/yum.repos.d view cloudera-manager.repo (change the https://archive.cloudera.com/cm5/redhat/7/x86_64/cm/5.16.1/ ) yum clean all yum update yum yum upgrade cloudera-manager-* Check on all Nodes : rpm -qa ¦ grep cloudera-manager-*
Check on all Nodes : rpm -qa ¦ grep cloudera-manager-*
Restart Mysql service mysqld restart (Just before restarting the server and agent) ITSUSRALSP07969.jnj.com and ITSUSRALSP08030.jnj.com
On itsusralsp07966.jnj.com start the server service cloudera-scm-server status service cloudera-scm-server start service cloudera-scm-server status
Start agents on all the servers: service cloudera-scm-agent status service cloudera-scm-agent start service cloudera-scm-agent status
Login to CM and then check for the CM version.
Install CDH parcels 5.15.2-1.cdh5.15.2.p0.3 activate and distribute
NOTE: Not to do upgrade cluster after we login to CM. This will upgrade the CDH version to 5.13.0
Open CM and login
Upgrade the CDH
Perform the EDL Basic Testing
BICC to perform the Basic Testing and confirm - Send out a mail to all BICC teams
Project teams to perform the basic testing and send confirmation - Send out a mail to all app teams
Send the final Service advisory completion
Check and make sure that the Navigator upgrade is complete
Clear browser cache for Hue - Add this in service advisory - completion
"service postfix restart" on all the nodes
keytool -import -alias tomcat -file /opt/cloudera/security/CAcerts/combinedtrust.pem -keystore /usr/java/latest/jre/lib/security/cacerts
increase heap size for Spark and spark2 Java Heap Size of History Server in Bytes = 1 GIB
Hue Service Advanced Configuration Snippet (Safety Valve) for hue_safety_valve.ini: [[ldap]] ignore_username_case=true force_username_lowercase=true sync_groups_on_login=true

## Post-Upgrade
S.No. | Action Item
1 | Steps to convert MySAM to INNODB: (Only if required. Only if error comes up in Hue) Remove blanks from oozie workflows: select count(*) FROM desktop_document WHERE NAME='' AND content_type_id=15 delete FROM desktop_document WHERE NAME='' AND content_type_id=15 To look at locks in the mysql database: show processlist; Stop the cluster services Stop the CM services Stop cloudera-scm-server Generate an SQL file: mysql -u root -p hue -e "SELECT CONCAT('ALTER TABLE ',table_schema,'.',table_name,' engine=InnoDB;') FROM information_schema.tables WHERE engine = 'MyISAM' and table_schema = 'hue';" ¦ grep "ALTER TABLE hue" > /tmp/migrate_to_innodb.sql Modify the database: mysql -u root -p hue < /tmp/migrate_to_innodb.sql Start cloudera-scm-server Start the CM services Start the cluster services | not required
2 | Capture API out in a txt file: https://itsusraedlq01.jnj.com:7183/api/v13/cm/deployment | done
3 | Do a file compare of the API output taken before the upgrade and after the upgrade for discrepancies | done
4 | Certificate for Hue: Case 117649 - Not able to login to HUE (Only if required) File is in dev d01 at /home/aomtri/junk/hue 1) Download InstallCert.txt from the case and rename it to InstallCert.java 2) Copy InstallCert.java to /tmp on the Hue host. 3) Run the following commands: cd /tmp export JAVA_HOME=/usr/java/jdk1.7.0_80/ export PATH=$JAVA_HOME/bin:$PATH javac InstallCert.java java InstallCert jnj.com:3269 4) Select highest number available. 5) Extract the downloaded cert from /tmp/jssecacerts. /usr/java/jdk1.7.0_67-cloudera/bin/keytool -exportcert -keystore /tmp/jssecacerts -alias jnj.com-2 -storepass changeit -file foo-2.cert 6) Convert the certificate to pem format. openssl x509 -inform der -in foo-2.cert >> /opt/cloudera/security/CAcerts/installcert.pem 7) Point 'Hue > LDAP Server CA Certificate' to /opt/cloudera/security/CAcerts/installcert.pem | not required
5 | Optional if KMS is running: Do not do for DEV, QA and PROD Download jce_policy-8.zip Unzip the file cp /home/aomtri/junk/UnlimitedJCEPolicyJDK8/*.jar /usr/java/latest/jre/lib/security/. [root@itsusmpl00645:/usr/java/latest/jre/lib/security]# #-> cp /home/aomtri/junk/UnlimitedJCEPolicyJDK8/*.jar . [root@itsusmpl00645:/usr/java/latest/jre/lib/security]# #-> ls -ltr total 152 -rw-r--r-- 1 root root 0 Aug 4 2015 trusted.libraries -rw-r--r-- 1 root root 98 Aug 4 2015 javaws.policy -rw-r--r-- 1 root root 23881 Aug 4 2015 java.security -rw-r--r-- 1 root root 2466 Aug 4 2015 java.policy -rw-r--r-- 1 root root 99954 Aug 4 2015 cacerts -rw-r--r-- 1 root root 1188 Aug 4 2015 blacklisted.certs -rw-r--r-- 1 root root 4054 Aug 4 2015 blacklist -rw-r--r-- 1 root root 3023 Jan 24 15:00 US_export_policy.jar -rw-r--r-- 1 root root 3035 Jan 24 15:00 local_policy.jar | not required
6 | Provide informatica the below xml's after the upgrade core-site.xml hdfs-site.xml hive-site.xml mapred-site.xml yarn-site.xml
7 | Un comment all the crontabs in all the nodes | done
8 | Testing: Teragen: yarn jar /opt/cloudera/parcels/CDH/lib/hadoop-0.20-mapreduce/hadoop-examples.jar teragen -Dmapred.map.tasks=28 -Ddfs.replication=1 10000000000 terasort-input Terasort: yarn jar /opt/cloudera/parcels/CDH/lib/hadoop-0.20-mapreduce/hadoop-examples.jar terasort terasort-input terasort-output Teravalidate: yarn jar /opt/cloudera/parcels/CDH/lib/hadoop-0.20-mapreduce/hadoop-examples.jar teravalidate Hue config check Hue Hive editor - Run queries Hue Impala Editor - Run queries Hue Solr Indexes Hue Hbase collections Hue Sentry setup and URI check Hue Oozie dashboard Navigator Metadata and Audit Resource Manager Links working or not Logs access from CM for all services Spark History UI check HDFS commands using individual user id's Sqoop run: sqoop import --connect jdbc:mysql://10.38.4.24/hue --username sqoopuser --password changeit --table auth_permission --target-dir /user/kkirange/1213 -m 3 --split-by id --delete-target-dir | done
9 | Change the Navigator heap size back to the space we changed before upgrade | done
10 | Add back the Parcel Url's which are removed during upgrade | not required
11 | Add impersonation configs for information. Get the user id list from Informatica team | done
12 | Ask Informatica team to send a mail to all EDL - Infa users to remove :8020 from there hdfs connection string