## PreMigrationSteps
S.No | Action Item | When? | Comments
0 | CR for 1. Certificate creation 2. Cloudera manager , agents install 3. Encryption deployment 4. CDH deployment + config changes 5. BDR batches - CR QABI-DATALAKE APP000010020090 SBXBI-DATALAKE APP000010020094 DEVBI-DATALAKE APP000010020089 PRODBI-DATALAKE APP000010020091
1 | Prepare the cluster topology along with the VM sizes and upload it to share point | Day 1
2 | Create VIP for Impala, VIP should be edlimpaladev.jnj.com. SLA for them is roughly 2 days. So do this well in advance. Link to workaid: https://jnj.sharepoint.com/teams/EnterpriseDataLake/Data%20Migration/Forms/AllItems.aspx?RootFolder=%2Fteams%2FEnterpriseDataLake%2FData%20Migration%2FWork%20Aid&FolderCTID=0x012000698F48B326C10E45B0C23B2D35F69E0B&View=%7B74B38FD1-BD30-4394-A141-1A1C87CE3025%7D | Day 1
3 | Create F5 request for Impala load balancer. Link to workaid: https://jnj.sharepoint.com/teams/EnterpriseDataLake/Data%20Migration/Forms/AllItems.aspx?RootFolder=%2Fteams%2FEnterpriseDataLake%2FData%20Migration%2FWork%20Aid&FolderCTID=0x012000698F48B326C10E45B0C23B2D35F69E0B&View=%7B74B38FD1-BD30-4394-A141-1A1C87CE3025%7D Mapping: First request should have these host names pointing to the load balancer ITSUSRALSP07809 ITSUSRALSP07810 ITSUSRALSP07811 ITSUSRALSP07812 ITSUSRALSP07813 Second request should have these hostnames point to the load balancer: This request should be implemented only during the cutover We add itsusraedld02.jnj.com itsusraedld03.jnj.com itsusraedld04.jnj.com and remove ITSUSRALSP07809 ITSUSRALSP07810 ITSUSRALSP07811 | Day 3 | VIP name should be ready
4 | Apply for login and temp root access to all the nodes in the dev cluster | Day 1
5 | Create a request to add nodes in the dev zone and dev edge zone. Here is the mapping. Link to workaid: https://jnj.sharepoint.com/teams/EnterpriseDataLake/Data%20Migration/Forms/AllItems.aspx?RootFolder=%2Fteams%2FEnterpriseDataLake%2FData%20Migration%2FWork%20Aid&FolderCTID=0x012000698F48B326C10E45B0C23B2D35F69E0B&View=%7B74B38FD1-BD30-4394-A141-1A1C87CE3025%7D Add nodes ITSUSRALSP07805 ITSUSRALSP07806 ITSUSRALSP07807 ITSUSRALSP07808 ITSUSRALSP07809 ITSUSRALSP07810 ITSUSRALSP07811 ITSUSRALSP07812 ITSUSRALSP07813 in ITSEDLDEV-LINUX-NA and ITSUSRALSP07814 in ITSEDLDEVEDGE-LINUX-NA | Day 1
| Once the nodes are added to the zones. Create a request with AD to delete http/hostname and http/hostname.jnj.com principals from AD. Cluster install can begin only if this is completed. CM install can still go forward. Link to the workaid: https://jnj.sharepoint.com/teams/EnterpriseDataLake/Data%20Migration/Forms/AllItems.aspx?RootFolder=%2Fteams%2FEnterpriseDataLake%2FData%20Migration%2FWork%20Aid&FolderCTID=0x012000698F48B326C10E45B0C23B2D35F69E0B&View=%7B74B38FD1-BD30-4394-A141-1A1C87CE3025%7D | Day 6 | Point 5 has to complete
6 | Create a request for hostname swapping. Link to workaid: https://jnj.sharepoint.com/teams/EnterpriseDataLake/Data%20Migration/Forms/AllItems.aspx?RootFolder=%2Fteams%2FEnterpriseDataLake%2FData%20Migration%2FWork%20Aid&FolderCTID=0x012000698F48B326C10E45B0C23B2D35F69E0B&View=%7B74B38FD1-BD30-4394-A141-1A1C87CE3025%7D Here is the mapping ITSUSRALSP07806 (itsusraedld01.jnj.com) ITSUSRALSP07807 (itsusraedld06.jnj.com) ITSUSRALSP07809(itsusraedld02.jnj.com) ITSUSRALSP07810(itsusraedld03.jnj.com) ITSUSRALSP07811(itsusraedld04).jnj.com ITSUSRALSP07814(itsusraedld05.jnj.com) | Day 1
7 | Generate certificates for all the nodes provisioned. Include the impala load balancer name in the certificate. Link to the workaid: https://jnj.sharepoint.com/teams/EnterpriseDataLake/Data%20Migration/Forms/AllItems.aspx?RootFolder=%2Fteams%2FEnterpriseDataLake%2FData%20Migration%2FWork%20Aid&FolderCTID=0x012000698F48B326C10E45B0C23B2D35F69E0B&View=%7B74B38FD1-BD30-4394-A141-1A1C87CE3025%7D | Day 2
9 | Install java in all the nodes of the cluster Sample steps: Change as needed mkdir /apps/java cd /usr ln -s /apps/java /usr/java mv /home/pthomas1/jdk-8u74-linux-x64.tar.gz /apps/java/. cd /usr/java tar -xvzf jdk-8u74-linux-x64.tar.gz cd /usr/java/jdk1.8.0_74/ alternatives --install /usr/bin/java java /usr/java/jdk1.8.0_74/bin/java 2 java -version cd .. chown root:root jdk-8u74-linux-x64.tar.gz chown -R root:root jdk1.8.0_74 ln -s /apps/java/jdk1.8.0_74/ /usr/java/latest ls -al java -version | Day 2
10 | Add cloudera-manager.repo to all the nodes in /etc//yum.repos.d/ Contents should be: [cloudera-manager] # Packages for Cloudera Manager, Version 5, on RedHat or CentOS 7 x86_64 name=Cloudera Manager baseurl=https://archive.cloudera.com/cm5/redhat/7/x86_64/cm/5.15.0/ gpgkey =https://archive.cloudera.com/cm5/redhat/7/x86_64/cm/RPM-GPG-KEY-cloudera gpgcheck = 1 | Day 2
11 | Execute "yum clean all" in all the nodes | Day 2
12 | Execute "yum update yum" in all the nodes | Day 2
13 | Install Cloudera manager server in one node of the cluster. Refer the topology to get the right node. Command is "yum install cloudera-manager-agent" | Day 2
14 | Install Cloudera manager agent in all the nodes of the cluster. Command is "yum install cloudera-manager-agent" | Day 2
15 | Create certificates required for cloudera manager agents and servers Sample commands: Change as required mkdir /opt/cloudera/security/jks mkdir /opt/cloudera/security/CACerts mkdir /opt/cloudera/security/x509 chown root:root /opt/cloudera/security chmod 755 /opt/cloudera/security chmod 755 /opt/cloudera/security/jks chown root:root /opt/cloudera/security/jks chown root:root /opt/cloudera/security/CAcerts chown root:root /opt/cloudera/security/x509 cd /opt/cloudera/security/jks/ cp /home/pthomas1/chromeissue/itsusralsp07674.pem server.pem chmod 444 server.pem ls -al cp /home/pthomas1/chromeissue/itsusralsp07674_jnj_com.key server.key chmod 440 server.key cp /home/pthomas1/truststore.jks /opt/cloudera/security/jks chown root:root /opt/cloudera/security/jks/truststore.jks chmod 644 /opt/cloudera/security/jks/truststore.jks cp /home/pthomas1/chromeissue/keystore.jks server.keystore chmod 444 server.keystore chown root:root server.keystore Copy combinedtrust.pem file from the old cluster into the new cluster. Use the same file. Create a new combinedtrust_chrome.pem file based on the steps in the workaid. Link: These 4 files should be available /opt/cloudera/security/x509/server.pem /opt/cloudera/security/x509/server.key /opt/cloudera/security/x509/serverkey.pw /opt/cloudera/security/CAcerts/combinedtrust.pem /opt/cloudera/security/CAcerts/combinedtrust_chrome.pem | Day 2
16 | Copy /etc/cloudera-scm-agent/config.ini file from itsusraedld01.jnj.com into the new CM node and modify it to point to the new CM host | Day 2
17 | Copy this config.ini file from this CM node into all the nodes in the cluster. Rename the existing config.ini file as a backup file | Day 2
18 | Start cloudera manager server with this command: "service cloudera-scm-server start" | Day 2
19 | Start cloudera manager agents on all the nodes with this command: "service cloudera-scm-agent start" | Day 2
20 | Open this URL for CM: http://itsusralsp07805:7180/cmf/login. This initial link will not have SSL enabled. We will have to update the CM configs within cloudera manager to enable SSL. | Day 2
21 | Login to CM using admin/admin as the initial username and password | Day 2
22 | Add "/opt/cloudera/security/jks/server.keystore" in Cloudera Manager TLS/SSL Server JKS Keystore File Location | Day 2
23 | Add the password for the keystore in "Cloudera Manager TLS/SSL Server JKS Keystore File Password" | Day 2
24 | Add "/opt/cloudera/security/jks/truststore.jks" in "Cloudera Manager TLS/SSL Certificate Trust Store File" | Day 2
25 | Add the password for the truststore in "Cloudera Manager TLS/SSL Certificate Trust Store Password" | Day 2
25 | Restart cloudera manager server with this command: service cloudera-scm-server restart | Day 2
26 | Open the CM link using this URL: https://itsusralsp07805:7183/cmf/login | Day 2
27 | Cluster install can now being | Day 2
28 | Do this for all nodes in the new cluster: Download jce_policy-8.zip Unzip the file cp /home/aomtri/junk/UnlimitedJCEPolicyJDK8/*.jar /usr/java/latest/jre/lib/security/. [root@itsusmpl00645:/usr/java/latest/jre/lib/security]# #-> cp /home/aomtri/junk/UnlimitedJCEPolicyJDK8/*.jar . [root@itsusmpl00645:/usr/java/latest/jre/lib/security]# #-> ls -ltr total 152 -rw-r--r-- 1 root root 0 Aug 4 2015 trusted.libraries -rw-r--r-- 1 root root 98 Aug 4 2015 javaws.policy -rw-r--r-- 1 root root 23881 Aug 4 2015 java.security -rw-r--r-- 1 root root 2466 Aug 4 2015 java.policy -rw-r--r-- 1 root root 99954 Aug 4 2015 cacerts -rw-r--r-- 1 root root 1188 Aug 4 2015 blacklisted.certs -rw-r--r-- 1 root root 4054 Aug 4 2015 blacklist -rw-r--r-- 1 root root 3023 Jan 24 15:00 US_export_policy.jar -rw-r--r-- 1 root root 3035 Jan 24 15:00 local_policy.jar | Day 2
29 | Prepare an excel for BDR with every database and folder that needs to be copied with checksum
31 | Raise a request for mutt installation in all the nodes in the cluster
32 | Raise a request for the linux team to modify : /etc/centrifydc/centrifydc.conf to remove http from adclient.krb5.service.principals
33 | Set krb5debug: Command: export KRB5_TRACE=/dev/stdout curl -v -u : --negotiate https://itsusralsp07886.jnj.com:8044/node/containerlogs/container_e77_1538328126576_26643_01_000003/sascmxed/stderr?start=-4096
For Reference: https://www.cyberciti.biz/tips/rebuilding-corrupted-rpm-database.html
Remove /var/lib/rpm/__db* files to avoid stale locks: # cd /var/lib # rm __db* Rebuild RPM database: # rpm --rebuilddb # rpmdb_verify Packages
1 | Remove http - Please remove http from adclient.krb5.service.principals in /etc/centrifydc/centrifydc.conf for the below mentioned servers permanently QA: RITM000015515147 RITM000015515161 RITM000015515169 DEV: RITM000015527073 RITM000015527080 RITM000015527086 SBX: RITM000015527459 RITM000015527461 PROD: RITM000015527482 RITM000015527484 RITM000015527487 RITM000015527493 RITM000015527510
2 | Delete http QA: RITM000015515402
3 | Please set /proc/sys/vm/swappiness to 10 permanently. This value should be 10 even if the server is rebooted by linux for any reason. QA: RITM000015515350 RITM000015515382 RITM000015515402 DEV: RITM000015527098 RITM000015527109 RITM000015527134 SBX: RITM000015527452 RITM000015527454 PROD: RITM000015527513 RITM000015527523 RITM000015527536 RITM000015527540 RITM000015527545
4 | Disable THP: Please disable transparent huge pages permanently in QA: RITM000015515288 RITM000015515297 RITM000015515310 DEV: RITM000015527221 RITM000015527230 RITM000015527234 SBX: RITM000015527447 RITM000015527450 PROD: RITM000015527621 RITM000015527629 RITM000015527633 RITM000015527646 RITM000015527649
5 | Add servers to zones: QA: REQ000014904601 SBX: RITM000015505557
6 | F5 load balancer request QA: RITM000015520825 DEV: RITM000015521261 RITM000015524896 RITM000015521280
7 | Lockfile request: QA: RITM000015521561 RITM000015521574 RITM000015521583
8 | CPU and Memory increase for QA - SDDC request QA: RITM000015521405 RITM000015521414 RITM000015521418 RITM000015521433 RITM000015521442 RITM000015521481 RITM000015521487 RITM000015521498 RITM000015521503 RITM000015521512 RITM000015521516 RITM000015521521 RITM000015521527
9 | More servers in PROD - Data nodes request for Mike
10 | IPAM - RITM000015521311 , RITM000015520914
11 | umask QA: RITM000015537345 umask PROD: RITM000015537356
12 | krb5-workstation install in all the nodes
13 | ulimit -n from 4096 to 16384 Prod: RITM000015547204 RITM000015547235 New DEV: RITM000015547280 QA: RITM000015547299

## ClusterInstallSteps
| S.No | Action Item | When? | Comments
| 1 | Open the CM link using this URL: https://itsusralsp07805:7183/cmf/login | Day 7
| 2 | Upload the license for the dev cluster in CM | Day 7
| 3 | Use the service placements from the topology excel uploaded in the share point link: https://jnj.sharepoint.com/teams/EnterpriseDataLake/Data%20Migration/Forms/AllItems.aspx?RootFolder=%2Fteams%2FEnterpriseDataLake%2FData%20Migration%2FWork%20Aid&FolderCTID=0x012000698F48B326C10E45B0C23B2D35F69E0B&View=%7B74B38FD1-BD30-4394-A141-1A1C87CE3025%7D File name for the topology for dev is EDL_NewDEVClusterTopology.xlsx | Day 7
| 4 | Click on the parcels icon in CM and open configuration. Remove the generic CDH parcels link and update it with this "https://archive.cloudera.com/cdh5/parcels/5.11.2/" and add the spark2 parcel link as well: "http://archive.cloudera.com/spark2/parcels/2.2.0.cloudera2/" | Day 7
| 5 | Install the spark 2 CSD - Custome Service Descriptor - https://www.cloudera.com/documentation/spark2/2-0-x/topics/spark2_installing.html | Day 7
| 6 | Add the below mentioned services in the cluster using this link as reference: http://www.cloudera.com/documentation/enterprise/latest/topics/cluster_setup_wizard.html Flume Hbase HDFS Hive Hue Impala Oozie Solr Spark Spark2 Sqoop1 client YARN Zookeeper | Day 7
| 7 | Create symlinks for all /var/lib/ and /var/log folders related to the cluster to /apps/lib and /apps/log | Day 7
| 8 | Change the configuration of all the services to point to /apps/heapdumpdir for the heap dump directory and restart the services | Day 7
| 9 | Enable HA in HDFS | Day 7
| 10 | Enable kerberos in the cluster using the CM wizard using this link as reference: https://www.cloudera.com/documentation/enterprise/5-11-x/topics/cm_sg_intro_kerb.html | Day 7
| 11 | Add sentry service in the cluster and enable sentry in solr, hive and hdfs services and restart the cluster | Day 7
| 12 | Enable TLS in all the services of the cluster except Hive and restart the cluster | Day 7
| 13 | Tune YARN for the right memory and container size | Day 7
| 14 | Retune the heap size used for all the services in the cluster | Day 7
| 15 | Setup data at rest encryption in the cluster using this link as reference: https://www.cloudera.com/documentation/enterprise/5-11-x/topics/encryption_ref_arch.html#concept_npk_rxh_1v | Day 7
| 16 | Enable snapshots for every project level folder in HDFS | Day 7
| 17 | Ensure all custom config changes in all the services are moved over to the new cluster | Day 7
| 18 | Install querygrid in the cluster: Refer to workaid for the installation instructions | Day 7
| 19 | Copy over all sentry grants from old cluster to the new cluster | Day 8
| 20 | Copy /usr/java/jdk1.8.0_74/jre/lib/security/US_export_policy.jar and /usr/java/jdk1.8.0_74/jre/lib/security/local_policy.jar from itsusralsp07611 to your local folder. Execute this on all nodes. This is for JCE in java. Change the command for your local node rm -rf /usr/java/jdk1.8.0_74/jre/lib/security/US_export_policy.jar; cp /home/pthomas1/US_export_policy.jar /usr/java/jdk1.8.0_74/jre/lib/security/US_export_policy.jar; chmod 777 /usr/java/jdk1.8.0_74/jre/lib/security/local_policy.jar; ls -al /usr/java/jdk1.8.0_74/jre/lib/security/US_export_policy.jar rm -rf /usr/java/jdk1.8.0_74/jre/lib/security/local_policy.jar; cp /home/pthomas1/local_policy.jar /usr/java/jdk1.8.0_74/jre/lib/security/local_policy.jar; chmod 777 /usr/java/jdk1.8.0_74/jre/lib/security/local_policy.jar; ls -al /usr/java/jdk1.8.0_74/jre/lib/security/local_policy.jar
| 21 | Add hdfs in yarn whitelist. Remove hdfs from yarn banned list and add parallel bdr configs in HDFS configuration HDFS Client Advanced Configuration Snippet (Safety Valve) for hdfs-site.xml (Add this both in the source and destination cluster) distcp.enable.listing.parallel true For parallel BDR distcp.fetch.threads 80 For parallel BDR dfs.client.block.write.locateFollowingBlock.retries 10 for fixing the issue -does not have enough number of replicas.
| 22 | Complete Hive and HDFS full BDR for all projects in the cluster. Execute in parallel so as to consume all the CPU cores in the new cluster | Day 9 to 14 | Started at 10pm EST, 18th Sept
| 23 | Testing: Teragen: yarn jar /opt/cloudera/parcels/CDH/lib/hadoop-0.20-mapreduce/hadoop-examples.jar teragen -Dmapred.map.tasks=28 -Ddfs.replication=1 10000000000 terasort-input Terasort: yarn jar /opt/cloudera/parcels/CDH/lib/hadoop-0.20-mapreduce/hadoop-examples.jar terasort terasort-input terasort-output Teravalidate: yarn jar /opt/cloudera/parcels/CDH/lib/hadoop-0.20-mapreduce/hadoop-examples.jar teravalidate Hue config check Hue Hive editor - Run queries Hue Impala Editor - Run queries Hue Solr Indexes Hue Hbase collections Hue Sentry setup and URI check Hue Oozie dashboard Navigator Metadata and Audit Resource Manager Links working or not Logs access from CM for all services Spark History UI check HDFS commands using individual user id's Sqoop run: sqoop import --connect jdbc:mysql://10.38.4.24/hue --username sqoopuser --password changeit --table auth_permission --target-dir /user/kkirange/1213 -m 3 --split-by id --delete-target-dir Also refer the workaid for additional steps | Day 14
| 24 | Add informatica impersonation configs | Day 8
| 25 | Copy encrypted data from old cluster to the new cluster | Day 8
| 26 | Create Hbase snapshots command before hand cutover day. It is time consuming
| 27 | Prepare solr snapshot commands before custover day. It is time consuming
| 28 | Temp hue access : Hive / Hive [desktop] http_500_debug_mode=1 django_debug_mode=1 secure_hsts_seconds=0 [[auth]] backend=desktop.auth.backend.LdapBackend,desktop.auth.backend.AllowFirstUserDjangoBackend [[ldap]] ignore_username_case=true force_username_lowercase=true [hbase] hbase_conf_dir={{HBASE_CONF_DIR}} [impala] close_queries=true server_host=itsusralsp07811.jnj.com query_timeout_s=600 session_timeout_s=1800 [beeswax] close_queries=true auth_username=saedlldd@JNJ.COM auth_password=LdapOnHive100 [hadoop] [[yarn_clusters]] [[[default]]] spark_history_server_url=https://itsusraedld01.jnj.com:18488
| 29 | Test Hive on LDAP connection string. Add the truststore file in HiveServer2 TLS/SSL Certificate Trust Store File to make sure hive with ldap works
| 30 | Make sure policy file sentry is enabled in oozie.
| 31 | keytool -import -alias tomcat -file /opt/cloudera/security/CAcerts/combinedtrust.pem -keystore /usr/java/latest/jre/lib/security/cacerts
| 32 | Check if postfix is running and use mailx command to test mails from all the servers
| 33 | Raise request for vm swapiness for linux tables
| 33 | keytool -importcert -keystore /apps/java/jdk1.8.0_74/jre/lib/security/cacerts -alias ldapcaa3 -storepass changeit -keypass Cloudera@5 -trustcacerts -file INT-PROD-CA-A3.cer keytool -importcert -keystore /apps/java/jdk1.8.0_74/jre/lib/security/cacerts -alias ldapcab3 -storepass changeit -keypass Cloudera@5 -trustcacerts -file INT_PROD-CA-B3.cer keytool -importcert -keystore /apps/java/jdk1.8.0_74/jre/lib/security/cacerts -alias ldapcac3 -storepass changeit -keypass Cloudera@5 -trustcacerts -file INT-PROD-CA-C3.cer keytool -importcert -keystore /apps/java/jdk1.8.0_74/jre/lib/security/cacerts -alias ldaproot2 -storepass changeit -keypass Cloudera@5 -trustcacerts -file INT-PROD-Root-2.cer keytool -importcert -keystore /apps/java/jdk1.8.0_74/jre/lib/security/cacerts -alias ldapt01 -storepass changeit -keypass Cloudera@5 -trustcacerts -file jnjinternalrootca.crt keytool -importcert -keystore /apps/java/jdk1.8.0_74/jre/lib/security/cacerts -alias ldapt02 -storepass changeit -keypass Cloudera@5 -trustcacerts -file jnjinternalonlinecaa2.crt keytool -importcert -keystore /apps/java/jdk1.8.0_74/jre/lib/security/cacerts -alias ldap -storepass changeit -keypass Cloudera@5 -trustcacerts -file ldapt01.cer For CM LDAP to work, the LDAP certificate needs to be imported into cacerts - java default cacerts. Refer the certs in itsusralsp07805
| 34 | Redo certificates in old cluster to include the IP address
35 | 35 | Global Messaging Team DL : hclgm@its.jnj.com - Enablel SMTP. Raise request for SMTP
| 36 | Add root and issuing to cacerts - default file
| 37 | hdfs dfs -chown -R yarn:supergroup /tmp/hadoop-yarn
| 38 | Oozie Server Advanced Configuration Snippet (Safety Valve) for oozie-site.xml - sync up with the old cluster
| 39 | LDAP in navigator
| 40 | Impala Daemons Load Balancer should be in this format: edlimpaladev.jnj.com:21057
| 41 | Send new certs to Informatica
| 42 | hdfs fsck -blockId blk_1079377242_5636491
| 43 | Create INFA_Pushdown_Hive INFA_Pushdown_Spark folder in all datanodes #-> hdfs dfs -setfacl -R -m default:group:its-app-edl-dev-proj12-etl-usr:rwx /app/INFA_Pushdown_Hive [root@ITSUSRALSP07814:/home/sbiswa25]# #-> hdfs dfs -setfacl -R -m group:its-app-edl-dev-proj12-etl-usr:rwx /app/INFA_Pushdown_Hive
| 44 | Copy over nav and navms database into the new mysql
| 45 | Impala Daemon Command Line Argument Advanced Configuration Snippet (Safety Valve) -force_lowercase_usernames=1 -fe_service_threads=128 -idle_session_timeout=1800 -convert_legacy_hive_parquet_utc_timestamps=true -idle_query_timeout=1800
| 46 | Set up YARN queues
| 47 | ln -s /apps/java/jdk1.8.0_74/ /usr/java/default
| 48 | Install anaconda parcels
| 49 | Install teradata connector parcels
| 50 | setspn -L hostname --- To check for http principals
| 51 | Set time zone in hue to America/New_York
| 52 | Spark history server redirection for chrome: 7. For each client that has connected to Hue you will need to clear the existing hsts record. The instructions for chrome are: a. Navigate to chrome://net-internals/#hsts b. At the bottom of the page in the "Delete domain security policies" section enter "itsusraedld01.jnj.com" and click "Delete" c. If you wish, you can confirm the hsts record has been deleted by entering "itsusraedld01.jnj.com" in the "Query HSTS/PKP domain" section and clicking "Query"
| 55 | Raise a request to install lockfile. It is in the standard JnJ packages. Subject is "RE: CHG000010440145 ¦¦ RITM000015491146"
| 56 | Point hive, oozie to impala load balancer
| 57 | YARN: Enable Fair Scheduler Continuous Scheduling - set it to false
| 58 | YARN: Fair Scheduler Assign Multiple Tasks - set it to true - enable check box
| 59 | Correct: "Oozie Server Advanced Configuration Snippet (Safety Valve) for oozie-site.xml" to "log4j.rootLogger=INFO,console log4j.appender.console=org.apache.log4j.ConsoleAppender log4j.appender.console.target=System.err log4j.appender.console.layout=org.apache.log4j.PatternLayout log4j.appender.console.layout.ConversionPattern=%d{yy/MM/dd HH:mm:ss} %p %c{2}: %m%n"
| 60 | Set "Auto Logout Timeout" for Hue to 20 minutes
| 61 | Oozie HA - call back configs in safety valve - ERICA issue
| 62 | UDF addition
| 63 | Sentry addition for all the projects

## CutoverSteps
S.No | Action Item | When? | Comments
1 | Take the name node backup: Look in all data volumes of the namenode cd /data/data01/dfs/nn tar -cvf nn_backup_data_nov04_2017.tar current
2 | Comment out the crontabs in ALL the nodes: #0 05,11,17,23 * * * sh -x /opt/BAR/Scripts/db_bkp.sh SCHM 2>&1 /app/EDL_Admin/Logs/runlog #0 * * * * > sh /opt/EDL_Admin/Spartan/Scripts/hueSync.sh > /opt/EDL_Admin/Spartan/Logs/hueSync.log #30 23,11 * * * sh -x /app/EDL_Admin/scripts/spacechecks/cdh_log_bkp.sh 60 7 2>&1 > /app/EDL_Admin/Logs/cdh_log_space.log #0 05,11,17,23 * * * sh -x /app/EDL_Admin/scripts/spacechecks/check_space.sh 80 80 2>&1 > /app/EDL_Admin/Logs/space_check.log
3 | Comment out PORTER: [saedlmia@itsusraedlq07:/root]# #-> crontab -l #1 0,6,12,18 * * * python /home/saedlmia/porter/porterMain.py > /home/saedlmia/porter/logs/dailyrun.log 2>&1 # 1 3,6,9,12,15,18 * * * python /home/saedlmia/porter/porterMain.py > /home/saedlmia/porter/logs/dailyrun.log 2>&1
4 | Take the MySQL Backup: sh -x /opt/BAR/Scripts/db_bkp.sh FULL 2>&1 /app/EDL_Admin/Logs/runlog
5 | Take the Navigator Backup In itsusraedld01.jnj.com: cp -r /app/lib/cloudera-scm-navigator /data/data03/navbackup/.
7 | Complete Hive incremental BDR for every project. Each BDR jobs should include the core, stg, wrk and archive databases
8 | Copy edge node local folders from the old edge node to the new edge node
9 | Copy all other node local folders from one cluster to another
10 | Complete HBase migration from one cluster to the other. Refer the steps available in the workaid.
11 | Complete Solr migration from one cluster to the other. Refer the steps available in the workaid.
12 | Complete Oozie migration from one cluster to the other. Refer the steps available in the workaid.
13 | Migrate Kudu data from one cluster to another. Refer the steps available in the workaid.
14 | Migrate CDSW from one cluster to another. Refer the steps available in the workaid.
15 | Ensure all housekeeping jobs are up and running
16 | Ensure the mysql back up is up and running
17 | Ensure porter is up and running
18 | Ensure all custom UDF's are added in hive and impala
19 | Ensure querygrid grant are available in sentry
20 | Compare with the old cluster and add all crontan entried related to EDL in all the nodes
21 | Spartan: /opt/EDL_Admin/Spartan/Scripts/main.sh needs to be moved
22 | Copy saved Hue queries from old cluster to new cluster
23 | Add YARN pool configs
24 | Sync hue ad groups - sh /opt/EDL_Admin/Spartan/Scripts/hueSync.sh > /opt/EDL_Admin/Spartan/Logs/hueSync.log >/dev/null 2>&1
24 | Symlink for /home folders in the edge node
25 | Addition in zookeeper for hbase? - Sharmila
26 | Connnect to CM database - scm -> update CONFIGS set value = 'false' where attr = 'telemetry_wa'; -> update CONFIGS set value = 'false' where attr = 'telemetry_master';
27 | Jay has suppressed web metric collection so we don't get errors on that web server status if the http principal is not deleted
28 | Hbase grant not working ================== Issue : ----------------- Hbase grant commands failing with below error : hbase(main):012:0> grant 'hive', 'RWXCA' ERROR: hbase:acl Grant users specific rights. Syntax : grant <user>, <permissions> [, <@namespace> [, <table> [, <column family> [, <column qualifier>]]] permissions is either zero or more letters from the set "RWXCA". READ('R'), WRITE('W'), EXEC('X'), CREATE('C'), ADMIN('A') Note: Groups and users are granted access in the same way, but groups are prefixed with an '@' character. In the same way, tables and namespaces are specified, but namespaces are prefixed with an '@' character. 2. same is working in other environments 3. In new hbase we cannot see anything in user_permission hbase(main):039:0> user_permission User Namespace,Table,Family,Qualifier:Permission we dont see any thing here but in dev we see hue user , hive user 4. In old DEV hbase(main):001:0> user_permission User Namespace,Table,Family,Qualifier:Permission hive hbase,hbase:acl,,: [Permission: actions=READ,WRITE,EXEC,CREATE] pthomas1 hbase,hbase:acl,,: [Permission: actions=READ,WRITE,EXEC,CREATE,ADMIN] user1 hbase,hbase:acl,,: [Permission: actions=READ,WRITE,CREATE] hue hbase,hbase:acl,,: [Permission: actions=READ,WRITE,EXEC,CREATE] impala hbase,hbase:acl,,: [Permission: actions=READ,WRITE,EXEC,CREATE] its-app-edl-prod-adm-dvlp-usr hbase,hbase:acl,,: [Permission: actions=READ,WRITE,EXEC,CREATE] 6 row(s) in 0.5100 seconds Troubleshooting : ----------------------------- go to hbase shell run scan hbase:acl it should error out hbase(main):008:0> scan hbase:acl NoMethodError: undefined method `hbase' for #<Object:0x7ec08115> Error log which indicate hbase:acl not created successfully: ------------------------------------------------------------ org.apache.hadoop.hbase.TableExistsException: hbase:acl at org.apache.hadoop.hbase.master.procedure.CreateTableProcedure.prepareCreate(CreateTableProcedure.java:302) at org.apache.hadoop.hbase.master.procedure.CreateTableProcedure.executeFromState(CreateTableProcedure.java:109) 18th September Error So the thing is, when we enabled security for Hbase, the hbase:acl table creation didnot go through Fix steps : ------------------- Option 1 : which we tried ========================== kinit as hbase on hbase master hbase hbck -fixOrphanedTableZnodes Restart Hbase run hbase shell run describe 'hbase:acl' scan 'hbase:acl' It failed Option 2 : which we tried ========================== 1.Go CM->Zookeeper->COnfigs->Java Options 2.Add this to Java Options,remove any additional spaces from end of the digest -Dzookeeper.DigestAuthenticationProvider.superDigest=super:cY+9eK20soteVC3fQ83SXDvwlP0=? Note : This may vary for QA and prod due to the key value , so check in Hbase logs first. Cloudera confirmed to delete this after Hbase grants are up. This is to create the hbase znode again on zookeeper the digest key after super: stands for cloudera we will add this digest in zookeeper as well, and then rmr the hbase hbase:acl table. so hbase will recreate it This is like authentication paswword we will use in zookeeeper cli to delete the znode like telling telling zk-cli that we have passwrd to delete as well 3.Rolling restart of zookeeper 4.Now login to zookeeper host, kinit 5.zookeeper-client ; zk> addauth digest super:cloudera ; 6. Stop Hbase 7.Come back to zk-client and run rmr /hbase/table/hbase:acl 8. Now start Hbase 9. Login to Master node , kinit with hbase, run hbase shell and run grants it should work now: hbase(main):004:0> grant 'hive', 'RWXCA' , '@addy_core' 0 row(s) in 0.3210 seconds hbase(main):005:0> grant '@its-app-edl-dev-proj52-supp-usr', 'RX', '@addy_core' 0 row(s) in 0.1140 seconds
29 | Hue db copy - Dump the Hue database to new cluster - http://www.cloudera.com/documentation/enterprise/5-11-x/topics/hue_dbs_migrate.html
30 | Hue - Authentication Backend was not set to LDAP
31 | #-> oozie jobs -oozie https://ITSUSRALSP07806.jnj.com:11443/oozie -localtime -len 2 -filter status=RUNNING
32 | Impala Daemon Command Line Argument Advanced Configuration Snippet (Safety Valve) -force_lowercase_usernames=1 -fe_service_threads=128 -idle_session_timeout=1800 -convert_legacy_hive_parquet_utc_timestamps=true -idle_query_timeout=1800
33 | Perfmon_core database - make sure this is added

## BICC Testing
S.No | Action Item | When? | Comments
1 | Ask Tableau to test their Impala ODBC connection and pull data for a sample report from DEV
2 | Ask Qlik to test their Impala ODBC connection and pull data for a sample report from DEV
3 | Ask Spotfire to test their Impala ODBC connection and pull data for a sample report from DEV
4 | Ask Teradata to test querygrid connectivity and run a query joining tables from Teradata and EDL
5 | Run a sqoop import and export to and from Teradata
6 | Informatica testing: 1. Informatica powercenter: write to hive, write to impala, write to kafka, write to hdfs, execute a sample mapping 2. Informatica BDM: Hive pushdown, Spark pushdown
7 | Test with Mbox to write to HDFS
8 | Test Talend connectivity
9 | Ask ITInsights to test their CICD setup with the new cluster
10 | Ask Agatha to test out SAP infosteward
11 | Ask Delphine to test out her ODBC connection connecting to new DEV
12 | Ask Niall and team to test out their scheduler in the new DEV cluster

## PostMigrationSteps
S.No | Action Item | When? | Comments
1 | Send out a service advisory for the new cluster after cutover. Create a PDF with all the links that need to be used. Update YAMMER as well
2 | Ask all application teams to test out
3 | Capture all the issues and resolve them

## IssueLogforDEV
Sno | Issue Name | Issue Description | Fix | Status | Remark
1 | BDR snapshots | BDR snapshots should just be enabled. Do not take actual snapshots. BDR will take it |  | Closed
2 | BDR snapshots | BDR snapshot should be enable only when the BDR is about to start |  | Closed
3 | Hive kerberos connection string issue |  |  | Closed
4 | Mbox testing
5 | Copy over /dev/admin data
6 | ISRM wrk and core databases are missing |  |  | Closed
7 | gdsn_STG, gdsn_wrk, gdsn_core missing
8 | Teradata connecter issue |  |  | Closed
9 | Solr ui issue
10 | Oozie host name change issue | oozie jobs -oozie https://itsusraedld01.jnj.com:11443/oozie -localtime -len 2 -filter status=RUNNING |  | Closed
11 | Remove TLS and kerberos in the old cluster |  |  | Closed
12 | hostname ¦ cut -c1-11 Before the migration the result was: itsusraedld However, now the result is: ITSUSRALSP0 |  |  | Closed
13 | Lesson learnt - What to do different
14 | Home folders scripts / data. What to we do? |  |  | Closed
15 | VIP for all the links | Hue, solr, oozie, hive, CM, RM, Navigator, Hbase, Kudu
16 | RHEL 7 - Regenerate keytabs for accounts with upper case |  |  | Closed
17 | Edge node permissions |  |  | Closed
18 | Conexa hive issue |  |  | Closed
19 | Cli1md jq issue |  |  | Closed
20 | Rack awareness - set it up
22 | Service advisory for impala load balancer |  |  | Closed
23 | PROD needs more storage for snapshots | Sai will create request for hostname in old dev and VIP requests for all services
24 | Mike to setup the request for QA and PROD servers
25 | Stakeholder call to discuss downtime for production
26 | RE: Issue with auth_user( ) UDF in DEV - UDF missing
27 | Issues from LeapFrog |  |  | Closed
28 | Issues from Hurricane |  |  | Closed
29 | Issues from CLi1md |  |  | Closed
30 | Lockfile missing in linux
31 | Mutt missing in linux
32 | Mails not working
33 | Loj4j error for Perumal - cli1md
34 | Mutt is not a standard package in JNJ
35 | Linux needs request created for 5 servers at a time
36 | Git setup not done in the edge node
37 | Python packages missing
38 | Keytabs not working - We are regenerating |  |  | Closed
39 | Conexa issue |  |  | Closed
40 | Tidal / control M jobs are working or not
41 | Supported packages - Chuck and Bhaskar
42 | Hadoop build - custom for linux
43 | Pre-requisites list for hadoop install
44 | 5 requests at a time
45 | Can you please check why we cannot use crontab anymore on the DEV Edge node. We use it to schedule our house cleaning jobs like removing old log files, etc. but neither sacnxaed nor sagbcsed are allowed to use it currently.
46 | Python libraries install
47 | FPR table metadata missing
48 | Cannot do QA/PROD in one shot
45 | Conda missing
46 | Solr issues while restoring snapshots
47 | Track who has tested and who has not tested
48 | Send - create the list of all TAO's
49 | Come up with the plan - for installation in PROD
50 | Tidal / ControlM - give them the edge node hostname and get a list of projects who have jobs
51 | Store MBOX keys in DEV, QA and PROD for sFTP
52 | Oozie mail - What to do?
53 | Missing databases - Double check

## PointofContact
iAware | Muthukrishnan, Rajaprakash [GTSUS Non-J&J] <RMuthukr@its.jnj.com>
TEDL | Seps, Jimmy [GTSC Extern] <JSEPS@its.jnj.com>, Gils, Charlotte [GTSC] <cgils1@ITS.JNJ.com>
CLSD | Kaushik, Amulya [JJCUS Non-J&J]
Updated for Tableau. Offshore: Subhra Onsite: Rubul
Updated for Qlik. Offshore: Srikanth Onsite: Sujith
Informatica : Gaurav Shah
GTS 2018 Q3 change freeze window is Monday, 24th September 2018 (12AM EST) to Friday, 5th October 2018 (11:59PM EST).

## Projects
S. No. | Project No. | App Name | App Owner | Biz Domain | Data Committed by the Project (TB)
Testing Status
1 | 1 | End To End Manufacturing (E2EMF) | Ashwin Rathnam (1008685) | Supply Chain | 2 | No
2 | 2 | Concur (EMW) | Prashant Bhanushali (1035300) | Finance | 2 | No
3 | 3 | Financial Planning & Analysis (FPNA) | Prashant Bhanushali (1035300) | Finance | 10 | WIP
4 | 4 | Process to Procure (P2P) | JAMES KIELAR (36198) | Finance | 1 | Yes
5 | 5 | Back to Basics (B2B) | Aaron MICHAEL PEERS(112415) | Supply Chain | 2 | WIP
6 | 8 | Erica | GIUSI NAPPI (22750400) | Supply Chain | 1 | No
7 | 9 | Crossplane (CRSPLN) | MARK LAY (151907) | Supply Chain | 1 | No
8 | 10 | Global Ortho Fidelity Analytics (GORA) | Judy Jiminez | Supply Chain | 14 | WIP
9 | 11 | Cost To Serve (CTS) | Sava Kostadinov (1009188) | Supply Chain | 3 | WIP
10 | 12 | Janssen Excellence Drive Initiation (iAware) - (JEDI) | BRYAN MCGRAW (340739) | Janssen R&D | 10 | Yes
11 | 13 | Food And Drug Administration Quality - DataBeat (FDA) | Marc Matrulli | Supply Chain | 1 | No
12 | 14 | IT Insights/IT Operations (ITOPS) | Wim Jacob | GTS | 20 | WIP
13 | 15 | JSC Destruction (JSDR) | MARSHALL BATDORF (185250) | Supply Chain | 1 | No
14 | 16 | One MD ECM (OVFA) | Rohit Chadda | Supply Chain | 1 | No
15 | 17 | EMS - UDI - Phase I (EMS) | WILLIAM HOERNLEIN JR ( 2382) | Supply Chain | 1 | WIP
16 | 20 | Consumer Next Generation (CNXA) | ACHIM URMERSBACH ( 203004480 ) | Consumer | 6 | WIP
17 | 21 | Leap Frog (LPFG) | Jason Bannister/Manesh Gunalan (417068) | Supply Chain | 10 | WIP
18 | 22 | Global APO stabilization (APOS) | Srikanth Atluri (1001175) | Medical Devices | 1 | WIP
19 | 23 | Transportation Data Lake (TDL) | Sreedhar Balasubramanian ( 1017513) | Supply Chain | 1 | WIP
20 | 25 | HCS Data Warehouse (HCSDW) | Michael Kondrof | Supply Chain | 1 | No
21 | 26 | Affiliate Gross Profit - Phase 1 (AGP) | Sheetal Jayan Pansare / Gurdeep Singh | Supply Chain | 2 | WIP
22 | 27 | SMART IT (SMIT) | Atul Sharma | GTS | 1 | Yes
23 | 29 | CLS DNA (CLSD) | CARLOS MIGUEL RIJO MOTA CALADO ( 25500375) | CLS Organization | 4 | Yes
24 | 34 | Complexity Analytics (CMAL) | LINGARAJ PANDA ( Raj Panda) (372202) | Supply Chain | 1 | No
25 | 40 | Consumer Plant Cockpit (VFCON) | Mario Hernandez/ Adrian Hale | Supply Chain | 1 | No
26 | 41 | Ethicon CSS Visual Factory (VFETH) | Savvas Pantazaras/ Adrian hale | Consumer | 1 | No
27 | 42 | QlikSense Implementation Cognos Dashboard (CMET) | Shiva Niranjan / Jimmy hennessey | Corporate | 1 | No
28 | 43 | Strategy Analytics Data Puddle (SADP) | Vidya Nagarkar | Supply Chain | 1 | No
29 | 44 | Johnson & Johnson Activity Repository (JJAR) | Bryan McGraw | CLS Organization | 1 | No
30 | 48 | Health Partner for Knees and Baraiatics (JJHWS) | Matthew Zaske (1047951) /SAURAV SARKAR (200629) | Consumer | 1 | No
31 | 49 | Cross Sector Order-to-Cash (CLSDIA) | Pramod Pacheeri (1040489) | CLS Organization | 4 | WIP
32 | 50 | EFM and WWETO DW and RPT (EFM) | Bill Frank/Bill Humani | Corporate | 3.5 | No
33 | 35 | Spitfire pilot Project (SPTFR) | Darren Thomas | Supply Chain | 3 | No
34 | 51 | OneMD - R&D Data Backbone (ONEMD) | Sumit Gupta | R&D | 3 | No
35 | 36 | PPMO | Himaja Yelagoila | Pharma | 3 | No
36 | 46 | Treasury Data Lake (TEDL) | Thijs Dieltjens | Corporate | 1 | WIP
37 | 52 | Instrument Analytics (ADDY) | Ashwin Ratnam | MD | 1 | No
38 | 31 | Global Ortho Finance - Slob (FPRSC) | Jackie O'Regan | Supply Chain | 1 | No
39 | 33 | BICC Monitoring Data (BICC) | Amit Kumar | GTS | 1 | WIP
40 | 28 | Data Pod for Sc E2E Analytics (SCE2E) | Dilip Hegde | Supply Chain | 1 | No
41 | 7 | Integration between PLcR & iAWARE(PLCR) | Steven Tufillaro | Pharma | 1 | No
42 | 32 | VC GQA Platform Upgrade (SDL) | Helen O'Malley | Supply Chain -MD | 1 | No
43 | 38 | CCI Phase 3 Remediation of CARS (CORE) | Michael Kondrof / Vandana Gangwani | MD | 1 | No
44 | 39 | OneMD Data Analytics (SCCSMD) | Timothy F. Riepl | Supply Chain -MD | 7 | No
45 | 45 | Global Tracking system for pre-approval Access (PAA) | Harish bevinhally | pharma | 1 | No
46 | 55 | Illicit Trade Analytics (GBP) | Peter Gonzalez | Supply Chain | 5 | WIP
47 | 56 | Prizma | Chuck Plate | Corporate | 1 | WIP
48 |  |  |  | Supply Chain -Consumer | 2 | WIP
49 | 59 | Global Medical Safety Data Lake (GSDL) | Jitendra Sinha | Supply Chain -RND | 1 | WIP
50 | 61 | MD Search Evidence (MDSE) | Ashish Kalra | MD | 3 | No
51 | 63 | Learning Data Warehouse - SUMMIT Phase 2 (LDW) | Robson De barros cavalcante | Corporate | 5 | No
52 | 64 | Project Compass (Performance Management Systems) (ESP) | Prasahnt Bhanusalli | Corporate | 1 | No
53 | 65 | One MD Clinical (CLI1MD) | Sumit Gupta | MD | 1 | WIP
54 | 54 | ATOM | Bitra Balaji | Supply Chain | 5 | WIP
55 | 66 | ESP (HR) | Prasahnt Bhanusalli | Corporate | 1 | No
56 | 67 | ESP (FIN) | Prasahnt Bhanusalli | Corporate | 1 | No
57 | 69 | ASPAC MD SCIT | Rajenikanth Anbanandan | Supply Chain -MD | 6 | No
58 | 70 | Medical Device GDSN automation for UK (Project Heartbeat) - (GDSN) | Gerald Schaedler | Supply Chain -MD | 3 | No
59 | 71 | PDS Data Analytics (PDSDA) | Serde Mukendi | Supply Chain -MD | 1 | No
60 | 73 | Talent Acquisition (TAM) | Vamseedhar | Corporate | 2 | No
61 | 75 | EPIIN | Jitendra Sinha | Pharma - RND | 0 | No
62 | 76 | Project Align - GTN Automation ( ALIGN) | Robert Devoe | Pharma | 1 | WIP
63 | 77 | ELIMS | Steven Van Hoof | Supply Chain - Pharma | 2 | No
64 | 78 |  | Daniel Junior | Supply Chain -MD | 1 | No
65 | 79 | SCML | Robert Chrzanowski | Supply Chain | 1 | No
66 | 80 | LIFT | Karen Vari | Pharma - RND | 1 | No
67 | 72 | DQTS | Robert Reid | Supply Chain -MD | 2
|  |  |  | Total Storage | 181.5
QA batches
Revised | [5 empty] | GXP
Batch 1 |  |  |  | Onsite | Offshore
mdse | 61 | MD Search Evidence (MDSE) | Ashish Kalra | Paul | Goutham
sc360 | 69 | ASPAC MD SCIT | Rajenikanth Anbanandan | Ajai | Shahnawaz
agp | 26 | Affiliate Gross Profit - Phase 1 (AGP) | Sheetal Jayan Pansare / Gurdeep Singh | Avinash | Shrenik | Y
align | 76 | Project Align - GTN Automation ( ALIGN) | Robert Devoe | Sharmila | Mubashir
apos | 22 | Global APO stabilization (APOS) | Srikanth Atluri (1001175) | Santhosh | Goutham
atom | 54 | ATOM | Bitra Balaji | Paul | Shahnawaz
epiin | 75 | EPIIN | Jitendra Sinha | Ajai | Shrenik
erica | 8 | Erica | GIUSI NAPPI (22750400) | Avinash | Mubashir
cli1md | 65 | One MD Clinical (CLI1MD) | Sumit Gupta | Sharmila | Goutham
clsdia | re | Cross Sector Order-to-Cash (CLSDIA) | Pramod Pacheeri (1040489) | Santhosh | Shahnawaz
cmal/smbc | 34 | Complexity Analytics (CMAL) | LINGARAJ PANDA ( Raj Panda) (372202) | Paul | Shrenik
core | 38 | CCI Phase 3 Remediation of CARS (CORE) | Michael Kondrof / Vandana Gangwani | Ajai | Mubashir
crspln | 9 | Crossplane (CRSPLN) | MARK LAY (151907) | Avinash | Goutham
cts | 11 | Cost To Serve (CTS) | Sava Kostadinov (1009188) | Sharmila | Shahnawaz
dqts | 72 | DQTS | Robert Reid | Santhosh | Shrenik
e2emf | 1 | End To End Manufacturing (E2EMF) | Ashwin Rathnam (1008685) | Paul | Mubashir
efm | 50 | EFM and WWETO DW and RPT (EFM) | Bill Frank/Bill Humani | Ajai | Goutham | Y
elims | 77 | ELIMS | Steven Van Hoof | Avinash | Shahnawaz
emw | 2 | Concur (EMW) | Prashant Bhanushali (1035300) | Sharmila | Shrenik
gbp | 55 | Illicit Trade Analytics (GBP) | Peter Gonzalez | Santhosh | Mubashir
ovfa | 16 | One MD ECM (OVFA) | Rohit Chadda | Paul | Goutham | Y
tedl | 46 | Treasury Data Lake (TEDL) | Thijs Dieltjens | Ajai | Shahnawaz
Batch 2
jedi | 12 | Janssen Excellence Drive Initiation (iAware) - (JEDI) | BRYAN MCGRAW (340739) | Avinash | Shrenik
addy | 52 | Instrument Analytics (ADDY) | Ashwin Ratnam | Sharmila | Mubashir
p2p | 4 | Process to Procure (P2P) | JAMES KIELAR (36198) | Santhosh | Goutham
esp | 64 | Project Compass (Performance Management Systems) (ESP) | Prasahnt Bhanusalli | Paul | Shahnawaz
b2b | 5 | Back to Basics (B2B) | Aaron MICHAEL PEERS(112415) | Ajai | Shrenik
fpr | 3 | Financial Planning & Analysis (FPNA) | Prashant Bhanushali (1035300) | Avinash | Mubashir
clsd | 29 | CLS DNA (CLSD) | CARLOS MIGUEL RIJO MOTA CALADO ( 25500375) | Sharmila | Goutham
gora | 10 | Global Ortho Fidelity Analytics (GORA) | Judy Jiminez | Santhosh | Shahnawaz
sadp | 43 | Strategy Analytics Data Puddle (SADP) | Vidya Nagarkar | Paul | Shrenik
sccsmd | 39 | OneMD Data Analytics (SCCSMD) | Timothy F. Riepl | Ajai | Mubashir
cnxa | 20 | Consumer Next Generation (CNXA) | ACHIM URMERSBACH ( 203004480 ) | Avinash | Goutham
hr | 66 | ESP (HR) | Prasahnt Bhanusalli | Sharmila | Shahnawaz
ldwsp | 63 | Learning Data Warehouse - SUMMIT Phase 2 (LDW) | Robson De barros cavalcante | Santhosh | Shrenik
lpfg | 21 | Leap Frog (LPFG) | Jason Bannister/Manesh Gunalan (417068) | Paul | Mubashir
ems | 17 | EMS - UDI - Phase I (EMS) | WILLIAM HOERNLEIN JR ( 2382) | Ajai | Goutham
sdl | 32 | VC GQA Platform Upgrade (SDL) | Helen O'Malley | Avinash | Shahnawaz
tdl | 23 | Transportation Data Lake (TDL) | Sreedhar Balasubramanian ( 1017513) | Sharmila | Shrenik
vfcon | 40 | Consumer Plant Cockpit (VFCON) | Mario Hernandez/ Adrian Hale | Santhosh | Mubashir
vfeth | 41 | Ethicon CSS Visual Factory (VFETH) | Savvas Pantazaras/ Adrian hale | Paul | Goutham
Batch 3
fda | 13 | Food And Drug Administration Quality - DataBeat (FDA) | Marc Matrulli | Ajai | Shahnawaz
paa | 45 | Global Tracking system for pre-approval Access (PAA) | Harish bevinhally | Avinash | Shrenik
pdsda | 71 | PDS Data Analytics (PDSDA) | Serde Mukendi | Sharmila | Mubashir
plcr | 7 | Integration between PLcR & iAWARE(PLCR) | Steven Tufillaro | Santhosh | Goutham
ppmo | 36 | PPMO | Himaja Yelagoila | Paul | Shahnawaz
prizma | 56 | Prizma | Chuck Plate | Ajai | Shrenik
prjpro | 58 | Project Pro (PRJPRO) | Stephanie Cooper | Avinash | Mubashir
fin | 67 | ESP (FIN) | Prasahnt Bhanusalli | Sharmila | Goutham
gdsn | 70 | Medical Device GDSN automation for UK (Project Heartbeat) - (GDSN) | Gerald Schaedler | Santhosh | Shahnawaz
gsdl | 59 | Global Medical Safety Data Lake (GSDL) | Jitendra Sinha | Paul | Shrenik
hcsdw | 25 | HCS Data Warehouse (HCSDW) | Michael Kondrof | Ajai | Mubashir
sce2e | 28 | Data Pod for Sc E2E Analytics (SCE2E) | Dilip Hegde | Avinash | Goutham
itops | 14 | IT Insights/IT Operations (ITOPS) | Wim Jacob | Sharmila | Shahnawaz
jjar | 44 | Johnson & Johnson Activity Repository (JJAR) | Bryan McGraw | Santhosh | Shrenik
sptfr | 35 | Spitfire pilot Project (SPTFR) | Darren Thomas | Paul | Mubashir
tam | 73 | Talent Acquisition (TAM) | Vamseedhar | Ajai | Goutham
lift | 80 | LIFT | Karen Vari | Avinash | Shahnawaz
onemd | 51 | OneMD - R&D Data Backbone (ONEMD) | Sumit Gupta | Sharmila | Shrenik
Hive hostname: edlhiveqa.jnj.com. Using LDAP as the connection string is recommended
Solr UI link: https://edlsolrqa.jnj.com:8985/solr/#/
Use edlhbaseqa.jnj.com for Hbase master connection
Use edloozieqa.jnj.com as the oozie server
Use this link for the resource manager link: https://edlrmsqa.jnj.com:8090/cluster
Use https://navigatorqa.jnj.com:7187/login.html for navigator
Use https://edljhsqa.jnj.com:19890/jobhistory as the YARN job history server
Use only mailx for mail generation via scripts
No git client will be installed in QA and PROD EDL edge nodes
All service accounts which have been created in UPPER CASE will have to have their keytabs regenerated
Automated migration from DEV to QA is no longer available
Change your tableau and qlik reports to point to the impala load balancer after you move over to the new cluster
If you are using Informatica, then make sure you are using the right connection strings. EDL support will be providing Informatica admins with the correct certificates and configs before hand.
Use edlhbasethriftqa.jnj.com for hbase thrift
Use edlhbaserestqa.jnj.com for HBase rest API’s
Hue link for QA EDL: https://edlhueqa.jnj.com:8888/
Impala load balancer host and port: edlimpalaqa.jnj.com. Port is 21000 for shell and 21050 for JDBC/ODBC
Spark history server UI link: https://edlsparkhistoryqa.jnj.com:18488/
Spark 2 history server UI link: https://edlspark2historyqa.jnj.com:18489/

## F5
DEV
edlhivedev.jnj.com | 10.39.4.56
edlsolrdev.jnj.com | 10.39.4.57
edlhbasedev.jnj.com | 10.39.4.58
edlooziedev.jnj.com | 10.39.4.59
edlcmdev.jnj.com | 10.39.4.60
edlrmsdev.jnj.com | 10.39.4.61
edlnavigatordev.jnj.com | 10.39.4.62
edlkududev.jnj.com | 10.39.4.63
edljhsdev.jnj.com | 10.39.4.64
edlhuedev.jnj.com | 10.39.4.113
edlspark2historydev.jnj.com | 10.39.4.114
edlsparkhistorydev.jnj.com | 10.39.4.115
edlimpaladev.jnj.com | 10.39.4.52
edlhbasethriftdev.jnj.com | 10.39.4.101
edlhbaserestdev.jnj.com | 10.39.4.102
QA |  | Port | Server1 | Server2 | Server3 | Server4 | Server5 | Server6 | Server7 | Server8
edlhiveqa.jnj.com | 10.39.4.74 | 10000 | ITSUSRALSP07936 | ITSUSRALSP07937
edlsolrqa.jnj.com | 10.39.4.75 | 8985 | ITSUSRALSP07939 | ITSUSRALSP07940 | ITSUSRALSP07941 | ITSUSRALSP07942 | ITSUSRALSP07943 | ITSUSRALSP07944 | ITSUSRALSP07945 | ITSUSRALSP07955
edlhbaseqa.jnj.com | 10.39.4.76 | 60010 | ITSUSRALSP07936 | ITSUSRALSP07937
edloozieqa.jnj.com | 10.39.4.77 | 11443 | ITSUSRALSP07936
edlcmqa.jnj.com | 10.39.4.103 | 7183 | ITSUSRALSP07935
edlrmsqa.jnj.com | 10.39.4.79 | 8090 | ITSUSRALSP07936 | ITSUSRALSP07937
edlnavigatorqa.jnj.com | 10.39.4.80 | 7187 | ITSUSRALSP07935
edlkuduqa.jnj.com | 10.39.4.81
edljhsqa.jnj.com | 10.39.4.82 | 19890 | ITSUSRALSP07938
edlhueqa.jnj.com | 10.39.4.116 | 8888 | ITSUSRALSP07935 | ITSUSRALSP07936 | ITSUSRALSP07937 | ITSUSRALSP07938 | ITSUSRALSP07939 | ITSUSRALSP07940 | ITSUSRALSP07941 |  | Edge node missing
edlspark2historyqa.jnj.com | 10.39.4.117 | 18489 | ITSUSRALSP07937
edlsparkhistoryqa.jnj.com | 10.39.4.118 | 18488 | ITSUSRALSP07936
edlimpalaqa.jnj.com | 10.39.4.119 | 21050/21000 | ITSUSRALSP07939 | ITSUSRALSP07940 | ITSUSRALSP07941 | ITSUSRALSP07942 | ITSUSRALSP07943 | ITSUSRALSP07944 | ITSUSRALSP07945 | ITSUSRALSP07955
edlhbasethriftqa.jnj.com | 10.39.4.99 | 9090 | ITSUSRALSP07936
edlhbaserestqa.jnj.com | 10.39.4.100 | 20550 | ITSUSRALSP07937
PROD
edlhiveprod.jnj.com | 10.39.4.86 | 10000 | ITSUSRALSP07967 | ITSUSRALSP07968 | ITSUSRALSP08030
edlsolrprod.jnj.com | 10.39.4.87 | 8985 | ITSUSRALSP07971 | ITSUSRALSP07973 | ITSUSRALSP07974 | ITSUSRALSP07975 | ITSUSRALSP07976 | ITSUSRALSP07977 | ITSUSRALSP07978 | ITSUSRALSP07979 | ITSUSRALSP07980 | ITSUSRALSP07981 | ITSUSRALSP07982 | ITSUSRALSP07983 | ITSUSRALSP07984 | ITSUSRALSP07985 | ITSUSRALSP07986 | ITSUSRALSP07987 | ITSUSRALSP07988 | ITSUSRALSP07989 | ITSUSRALSP07989 | ITSUSRALSP07990 | ITSUSRALSP08028 | ITSUSRALSP08027 | ITSUSRALSP08026 | ITSUSRALSP08024 | ITSUSRALSP08025
edlhbaseprod.jnj.com | 10.39.4.88 | 60010 | ITSUSRALSP07967 | ITSUSRALSP07968
edloozieprod.jnj.com | 10.39.4.89 | 11443 | ITSUSRALSP07967 | ITSUSRALSP07968
edlcmprod.jnj.com | 10.39.4.105 | 7183 | ITSUSRALSP07966
edlrmsprod.jnj.com | 10.39.4.91 | 8090 | ITSUSRALSP07967 | ITSUSRALSP07968
edlnavigatorprod.jnj.com | 10.39.4.92 | 7187 | ITSUSRALSP07966
edlkuduprod.jnj.com | 10.39.4.93
edljhsprod.jnj.com | 10.39.4.94 | 19890 | ITSUSRALSP08030
edlhueprod.jnj.com | 10.39.4.106 | 8888 | ITSUSRALSP07966 | ITSUSRALSP07967 | ITSUSRALSP07968 | ITSUSRALSP07969 | ITSUSRALSP08030 | ITSUSRALSP08023
edlspark2historyprod.jnj.com | 10.39.4.107 | 18489 | ITSUSRALSP07970
edlsparkhistoryprod.jnj.com | 10.39.4.108 | 18488 | ITSUSRALSP08030
edlimpalaprod.jnj.com | 10.39.4.109 | 21050/21000 | ITSUSRALSP07971 | ITSUSRALSP07973 | ITSUSRALSP07974 | ITSUSRALSP07975 | ITSUSRALSP07976 | ITSUSRALSP07977 | ITSUSRALSP07978 | ITSUSRALSP07979 | ITSUSRALSP07980 | ITSUSRALSP07981 | ITSUSRALSP07982 | ITSUSRALSP07983 | ITSUSRALSP07984 | ITSUSRALSP07985 | ITSUSRALSP07986 | ITSUSRALSP07987 | ITSUSRALSP07988 | ITSUSRALSP07989 | ITSUSRALSP07989 | ITSUSRALSP07990 | ITSUSRALSP08028 | ITSUSRALSP08027 | ITSUSRALSP08026 | ITSUSRALSP08024 | ITSUSRALSP08025
edlhbasethriftprod.jnj.com | 10.39.4.95 | 9090 | ITSUSRALSP07967
edlhbaserestprod.jnj.com | 10.39.4.96 | 20550 | ITSUSRALSP07968
SBX
edlhivesbx.jnj.com | 10.39.4.65
edlsolrsbx.jnj.com | 10.39.4.66
edlhbasesbx.jnj.com | 10.39.4.67
edlooziesbx.jnj.com | 10.39.4.68
edlcmsbx.jnj.com | 10.39.4.104
edlrmssbx.jnj.com | 10.39.4.70
edlnavigatorsbx.jnj.com | 10.39.4.71
edlkudusbx.jnj.com | 10.39.4.72
edljhssbx.jnj.com | 10.39.4.73
edlhuesbx.jnj.com | 10.39.4.110
edlspark2historysbx.jnj.com | 10.39.4.111
edlsparkhistorysbx.jnj.com | 10.39.4.112
edlimpalasbx.jnj.com | 10.38.169.18
edlhbasethriftsbx.jnj.com | 10.39.4.97
edlhbaserestsbx.jnj.com | 10.39.4.98

## Learnings
1 | Do the migration in batches
2 | BDR needs to have a strict checklist for the number of databases and folders
3 | BDR snapshots - When to set it up
4 | Solr migration - not smooth. Identify which projects can load data from the source
5 | Avoid last minute changes to the cluster before release
6 | Cluster requires multiple restarts when issues are identified
7 | Hbase move commands need to be finialized well before the actual move
8 | BICC has to be available
9 | What projects can do different? - Custom packages, custom code
10 | Service advisories - The exact to list including the TAO's - updated TAO's