## Pre-Upgrade
S.No. | Date | Action Item
1 | 2nd Dec 2017 | Apply for root access in Myapps for the QA server | done
2 |  | Calculate Navigator Metadata Server Heap Size for Upgrade Link: https://cloudera-portal.force.com/articles/KB_Article/Navigator-Metadata-Server-Exits-Unexpectedly-Heap-Size-Upgrade-Issue-TsP?popup=false&navBack=H4sIAAAAAAAAAIuuVipWslLyzssvz0lNSU_1yM9NVdJRygaKFSSmp4ZkluSA-KVAvn58aaZ-NkyhPpCDosu-ODWxKDnD1i-xLDM9sSS_SNs3tSQxJbEkUbs4tagstUg7IzWxQKk2FgDrDdwFcwAAAA | done
3 |  | Run Navigator clean up API's before upgrading CM and the cluster Steps: Purge API: curl -X POST -u 'userid:password' "https://itsusraedlq01.jnj.com:7187/api/v9/maintenance/purge?deleteTimeThresholdMinutes=43200" --cacert /opt/cloudera/security/CAcerts/combinedtrust.pem Status API: curl -X GET -u 'userid:password' "https://itsusraedlq01.jnj.com:7187/api/v9/maintenance/running" --cacert /opt/cloudera/security/CAcerts/combinedtrust.pem History API: curl -X GET -u 'userid:password' "https://itsusraedlq01.jnj.com:7187/api/v9/maintenance/history?offset=0&limit=100" --cacert /opt/cloudera/security/CAcerts/combinedtrust.pem | done
4 |  | kinit -kt /root/porter/configs/dev.hdfs.keytab hdfs/itsusraedlq01.jnj.com hdfs fsck / hdfs dfsadmin -report kinit -kt /home/asingh57/hbase.keytab hbase/itsusraedlq01.jnj.com hbase hbck kdestroy Check if there is anything missing or lost blocks | done
5 |  | Capture API output in a txt file: https://itsusraedlq01.jnj.com:7183/api/v16/cm/deployment | done
6 |  | Send out service advisory just before the upgrade | done
7 |  | Upload diagnostic bundle with a size of 2048 MB to Cloudera before the upgrade: Add comment "Before upgrade to CDH 5.11.2 / CM 5.13.0" in the diagnostic comments section | done
8 |  | Run a host inspector in CM before starting the upgrade. Capture the results. Download it and save | done
9 |  | Take SQL Backup after shutting down the cluster - Approximate run time 1.5 hours | done

## Upgrade CM Hour Plan
Date | StartTime | EndTime | Activity | Resources | Status | Comments for EDL upgrade
2nd Dec 2017 | 8am | 3pm | Make sure that the users are logged off and no jobs are running |  | done
|  |  | Shutdown the cluster services and cloudera manager services |  | done
|  |  | Stop CM server and agents in all the nodes, including the workbench node #-> ./runall.sh "hostname && service cloudera-scm-agent stop" #-> ./runall.sh "hostname && service cloudera-scm-agent status" #-> ./runall.sh "hostname && service cloudera-scm-server stop" #-> ./runall.sh "hostname && service cloudera-scm-server status" |  | done
|  |  | Take the MySQL Backup: sh -x /opt/BAR/Scripts/db_bkp.sh FULL 2>&1 /app/EDL_Admin/Logs/runlog |  | started
|  |  | Take NN Backup for both active n standby locate nn ¦ more cd /apps/dfs/nn/current if there is any backed up NN move it to upgrade folder tar -cvf /app/nnbackup/nn_bkp_02Dec2017_data01.tar . cd /home/kmanika/upgrade |  | done
|  |  | Java Upgrade on all the nodes to 1.8.74 |  | done
|  |  | Perform this step on Each nodes export LD_LIBRARY_PATH=/lib:/usr/lib cd /etc/yum.repos.d/ view cloudera-manager.repo (change the repo to 5.13.0 in all the nodes) yum clean all yum update yum yum upgrade cloudera-manager-* |  | done
|  |  | Check the yum repo steps from the below command ./runall.sh "hostname && rpm -qa ¦ grep cloudera-manager-*" |  | done
|  |  | Restart Mysql service mysqld restart (Just before restarting the server and agent) |  | done
|  |  | Restart the CM server and agent for all the nodes with below commands #-> ./runall.sh "hostname && service cloudera-scm-server start" #-> ./runall.sh "hostname && service cloudera-scm-agent start" /etc/init.d/mysqld start /etc/init.d/mysqld status #-> ./runall.sh "hostname && service cloudera-scm-agent status" #-> ./runall.sh "hostname && service cloudera-scm-server status" |  | done
|  |  | Login to CM and then check for the CM version. |  | done
NOTE: Not to do upgrade cluster after we login to CM. This will upgrade the CDH version to 5.13.0
For Reference: https://www.cyberciti.biz/tips/rebuilding-corrupted-rpm-database.html
Remove /var/lib/rpm/__db* files to avoid stale locks: # cd /var/lib # rm __db* Rebuild RPM database: # rpm --rebuilddb # rpmdb_verify Packages

## Upgrade CDH Hour Plan
Date | StartTime | EndTime | Activity | Resources | Status | Comments for EDL upgrade
2nd Dec 2017 | 8am | 3pm | Make sure that the users are logged off and no jobs are running and open this link: https://www.cloudera.com/documentation/enterprise/latest/topics/install_upgrade_to_cdh5x_parcels.html |  | done
|  |  | Take the name node backup: Look in all data volumes of the namenode cd /data/data01/dfs/nn tar -cvf nn_backup_data_nov04_2017.tar current |  | done | Link: https://www.cloudera.com/documentation/enterprise/5-8-x/topics/install_upgrade_to_cdh58_parcels.html#xd_583c10bfdbd326ba-590cb1d1-149e9ca9886--7a4d Search for "Back up the HDFS Metadata on the NameNode"
|  |  | Comment out the crontabs in ALL the nodes: #0 05,11,17,23 * * * sh -x /opt/BAR/Scripts/db_bkp.sh SCHM 2>&1 /app/EDL_Admin/Logs/runlog #0 * * * * > sh /opt/EDL_Admin/Spartan/Scripts/hueSync.sh > /opt/EDL_Admin/Spartan/Logs/hueSync.log #30 23,11 * * * sh -x /app/EDL_Admin/scripts/spacechecks/cdh_log_bkp.sh 60 7 2>&1 > /app/EDL_Admin/Logs/cdh_log_space.log #0 05,11,17,23 * * * sh -x /app/EDL_Admin/scripts/spacechecks/check_space.sh 80 80 2>&1 > /app/EDL_Admin/Logs/space_check.log |  | done
|  |  | Comment out PORTER: [saedlmia@itsusraedlq07:/root]# #-> crontab -l #1 0,6,12,18 * * * python /home/saedlmia/porter/porterMain.py > /home/saedlmia/porter/logs/dailyrun.log 2>&1 # 1 3,6,9,12,15,18 * * * python /home/saedlmia/porter/porterMain.py > /home/saedlmia/porter/logs/dailyrun.log 2>&1 |  | done
|  |  | Take the MySQL Backup: sh -x /opt/BAR/Scripts/db_bkp.sh FULL 2>&1 /app/EDL_Admin/Logs/runlog |  | done
|  |  | Take the Navigator Backup In itsusraedlq01.jnj.com: cp -r /app/lib/cloudera-scm-navigator /data/data03/navbackup/. |  | done
|  |  | Increase heap size of Navigator Metadata Server before CM upgrade |  | done | https://cloudera-portal.force.com/articles/KB_Article/Navigator-Metadata-Server-Exits-Unexpectedly-Heap-Size-Upgrade-Issue-TsP?popup=false&navBack=H4sIAAAAAAAAAIuuVipWslLyzssvz0lNSU_1yM9NVdJRygaKFSSmp4ZkluSA-KVAvn58aaZ-NkyhPpCDosu-ODWxKDnD1i-xLDM9sSS_SNs3tSQxJbEkUbs4tagstUg7IzWxQKk2FgDrDdwFcwAAAA
|  |  | Upgrade Java in all the nodes: 1. Upgrade java version to 1.8.0_74 http://www.cloudera.com/documentation/enterprise/5-8-x/topics/cdh_ig_jdk_installation.html#topic_29 cd /usr/java tar -xvzf jdk-8u74-linux-x64.tar.gz chown -R root:root jdk1.8.0_74 ls -al jdk1.8.0_74 ln -sfn /usr/java/jdk1.8.0_74 latest ln -sfn /usr/java/latest/bin/java /etc/alternatives/java /usr/sbin/alternatives --remove java /usr/lib/jvm/jre-1.5.0-gcj/bin/java |  | done
|  |  | Upgrade CM export LD_LIBRARY_PATH=/lib:/usr/lib cd /etc/yum.repos.d/ cat cloudera-manager.repo (change the repo to 5.13.0 in all the nodes) yum clean all yum update yum yum upgrade cloudera-manager-* |  | done
|  |  | service cloudera-scm-server start in nn service cloudera--scm-agent start in all the nodes |  | done
|  |  | Open CM and login |  | done
|  |  | Upgrade the CDH |  | done
|  |  | Perform the EDL Basic Testing |  | done
|  |  | BICC to perform the Basic Testing and confirm - Send out a mail to all BICC teams |  | done
|  |  | Project teams to perform the basic testing and send confirmation - Send out a mail to all app teams |  | sent out
|  |  | Send the final Service advisory completion |  | sent
|  |  | Check and make sure that the Navigator upgrade is complete |  | done
|  |  | Clear browser cache for Hue - Add this in service advisory - completion |  | done
|  |  | "service postfix restart" on all the nodes |  | done
|  |  | keytool -import -alias tomcat -file /opt/cloudera/security/CAcerts/combinedtrust.pem -keystore /usr/java/latest/jre/lib/security/cacerts |  | done

## Post-Upgrade
S.No. | Action Item
1 | Steps to convert MySAM to INNODB: (Only if required. Only if error comes up in Hue) Remove blanks from oozie workflows: select count(*) FROM desktop_document WHERE NAME='' AND content_type_id=15 delete FROM desktop_document WHERE NAME='' AND content_type_id=15 To look at locks in the mysql database: show processlist; Stop the cluster services Stop the CM services Stop cloudera-scm-server Generate an SQL file: mysql -u root -p hue -e "SELECT CONCAT('ALTER TABLE ',table_schema,'.',table_name,' engine=InnoDB;') FROM information_schema.tables WHERE engine = 'MyISAM' and table_schema = 'hue';" ¦ grep "ALTER TABLE hue" > /tmp/migrate_to_innodb.sql Modify the database: mysql -u root -p hue < /tmp/migrate_to_innodb.sql Start cloudera-scm-server Start the CM services Start the cluster services | not required
2 | Capture API out in a txt file: https://itsusraedlq01.jnj.com:7183/api/v13/cm/deployment | done
3 | Do a file compare of the API output taken before the upgrade and after the upgrade for discrepancies | done
4 | Certificate for Hue: Case 117649 - Not able to login to HUE (Only if required) File is in dev d01 at /home/aomtri/junk/hue 1) Download InstallCert.txt from the case and rename it to InstallCert.java 2) Copy InstallCert.java to /tmp on the Hue host. 3) Run the following commands: cd /tmp export JAVA_HOME=/usr/java/jdk1.7.0_80/ export PATH=$JAVA_HOME/bin:$PATH javac InstallCert.java java InstallCert jnj.com:3269 4) Select highest number available. 5) Extract the downloaded cert from /tmp/jssecacerts. /usr/java/jdk1.7.0_67-cloudera/bin/keytool -exportcert -keystore /tmp/jssecacerts -alias jnj.com-2 -storepass changeit -file foo-2.cert 6) Convert the certificate to pem format. openssl x509 -inform der -in foo-2.cert >> /opt/cloudera/security/CAcerts/installcert.pem 7) Point 'Hue > LDAP Server CA Certificate' to /opt/cloudera/security/CAcerts/installcert.pem | not required
5 | Optional if KMS is running: Do not do for DEV, QA and PROD Download jce_policy-8.zip Unzip the file cp /home/aomtri/junk/UnlimitedJCEPolicyJDK8/*.jar /usr/java/latest/jre/lib/security/. [root@itsusmpl00645:/usr/java/latest/jre/lib/security]# #-> cp /home/aomtri/junk/UnlimitedJCEPolicyJDK8/*.jar . [root@itsusmpl00645:/usr/java/latest/jre/lib/security]# #-> ls -ltr total 152 -rw-r--r-- 1 root root 0 Aug 4 2015 trusted.libraries -rw-r--r-- 1 root root 98 Aug 4 2015 javaws.policy -rw-r--r-- 1 root root 23881 Aug 4 2015 java.security -rw-r--r-- 1 root root 2466 Aug 4 2015 java.policy -rw-r--r-- 1 root root 99954 Aug 4 2015 cacerts -rw-r--r-- 1 root root 1188 Aug 4 2015 blacklisted.certs -rw-r--r-- 1 root root 4054 Aug 4 2015 blacklist -rw-r--r-- 1 root root 3023 Jan 24 15:00 US_export_policy.jar -rw-r--r-- 1 root root 3035 Jan 24 15:00 local_policy.jar | not required
6 | Provide informatica the below xml's after the upgrade core-site.xml hdfs-site.xml hive-site.xml mapred-site.xml yarn-site.xml
7 | Un comment all the crontabs in all the nodes | done
8 | Testing: Teragen: yarn jar /opt/cloudera/parcels/CDH/lib/hadoop-0.20-mapreduce/hadoop-examples.jar teragen -Dmapred.map.tasks=28 -Ddfs.replication=1 10000000000 terasort-input Terasort: yarn jar /opt/cloudera/parcels/CDH/lib/hadoop-0.20-mapreduce/hadoop-examples.jar terasort terasort-input terasort-output Teravalidate: yarn jar /opt/cloudera/parcels/CDH/lib/hadoop-0.20-mapreduce/hadoop-examples.jar teravalidate Hue config check Hue Hive editor - Run queries Hue Impala Editor - Run queries Hue Solr Indexes Hue Hbase collections Hue Sentry setup and URI check Hue Oozie dashboard Navigator Metadata and Audit Resource Manager Links working or not Logs access from CM for all services Spark History UI check HDFS commands using individual user id's Sqoop run: sqoop import --connect jdbc:mysql://10.38.4.24/hue --username sqoopuser --password changeit --table auth_permission --target-dir /user/kkirange/1213 -m 3 --split-by id --delete-target-dir | done
9 | Change the Navigator heap size back to the space we changed before upgrade | done
10 | Add back the Parcel Url's which are removed during upgrade | not required
11 | Add impersonation configs for information. Get the user id list from Informatica team | done
12 | Ask Informatica team to send a mail to all EDL - Infa users to remove :8020 from there hdfs connection string

## Issue Tracker
Sno | Issue Name | Issue Description | Fix | Status | Remark
1 | Oozie email action not working | Email actions were failing with error "org.apache.oozie.action.ActionExecutorException: EM007: Encountered an error while sending the email message over SMTP" | reverted oozie.email.smtp.host to localhost from itsusraedld01.jnj.com which was made during ugrade due to Warning in Hue welcome screen | Fixed | But after this change email action is working but the warning is still there in HUE
2 | Warning "Email notifications is disabled for Workflows and Jobs as SMTP server is localhost." appearing in HUE welcome screen | Warning "Email notifications is disabled for Workflows and Jobs as SMTP server is localhost." appearing in HUE welcome screen |  | Fixed | Cosmetic issue. No Impact
3 | .hive-staging directory getting created inside the table path whenever a table is created via HUE-hive | Whenever we run a query from hive , these temporary staging directories are created and are deleted as soon as the session is closed. But when we run from Hue , hive keeps it open so that one can view results of old queries aswell | Added following text in HUE safety valve configuration: [beeswax] close_queries=true | Fixed | But trick is you have to navigate to some other services in HUE then only these directories will be created.
4 | IT Insights spark compilation error | Spark jobs from IT Insights are not compiling properly after the upgrade | Project team needs to recompile with proper dependencies | Fixed | Was a local repo jars miss match issues.
5 | Hue hive and impala editor has a limitation of downloading upto 100,000 rows after the upgrade. Before the upgrade, there was no such limit | Some analysts download a lot of data from Hue. They are impacted | Run queries which limit the number of records to 100k or less. Or use the command line to pull this data | Fixed | This limit is in place to avoid Hue from hanging up. Hue is a browser based application and large downloads will slow this service down
6 | Hive shell shows a warning message when a query is executed. | Warning message interfers with logs | Use beeline shell | Fixed | Hive is deprecated. Users have been asked to use beeline
7 | Sentry database check | Authorization does not work properly | mysql -uroot -pCloudera@5 -e"select * from metastore.SDS" > /app/sdstablenew01.txt Check if there is // in the location field after hdfs://nameservice1 mysql -uroot -p use metastore; UPDATE SDS SET LOCATION = "hdfs://nameservice1/qa/edl/sc/b2b/str/b2b_stg/aspac/ap_t052" where SD_ID=1189898; | Fixed | Patch is available to prevent this issue. Will be implemented after the change freeze. After jan 8, 2018